## Cover Page
<Project Name>
Sprint Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
Name
Role
Signature
Date
:
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Sprint Backlog - Instructions C3: Protected Controlled Copy
Sprint Backlog
The Sprint Backlog is the set of Product Backlog items selected for the Sprint, plus a plan for delivering the product Increment and realizing the Sprint Goal. The Sprint Backlog is a forecast by the Development Team about what functionality will be in the next Increment and the work needed to deliver that functionality into a “Done” Increment.The Sprint Backlog is the output of the sprint planning meeting. It is essentially the list of tasks that the Scrum team needs to complete during the sprint in order to turn a selected set of product backlog items into a deliverable increment of functionality.
Sample
The sheet sample is an example sheet on how to fill the sprint backlog. Trainees can refer it to fill the details in the sheets Sprint 1/2/3.
Sprint 1/2/3
| User Story & Task Id | List the User Story id taken from product backlog that are selected to be completed in the particular sprint & List the number of tasks the User story is split into..
| Task | Name the tasks the user story is split into.
| Story Points | Enter the story points that was given for the user story during Sprint planning
| Assigned to | Name the person responsible for the particular task
| Status | Status of the Task - In progress/Completed
| Original Estimate | Original estimate of the task
| Day 1/2/3/4/5 | Task done in Day1/2/3/4/5 - Sprint review and retrospective to be held on Day 5
| Total | Summation of the estimation per day. To be filled with the total of the estimations filled.
| Charts | Chart is self driven as per the task burned

## Sample
Sprint Backlog <Project name> Project ID: <Batch code/project id> C3: Protected Controlled Copy
USER STORY & TASK ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
US_1 | User Registration | 8
Task_1 | Create table to store registration details |  | Trainee_1 |  | 7 | 5 | 3 | 0 | 0 | 0
Task_2 | Design the registration page |  | Trainee_2 |  | 3 | 1 | 1 | 5 | 0 | 1
Task_3 | Design Login page |  | Trainee_1 |  | 1 | 0.5 | 0 | 3 | 0 | 0
Task_4 | Develop authentication process for login |  | Trainee_2 |  | 0.5 | 1 | 2 | 3 | 1 | 0
US_2 | Admin Home | 1
Task_1 | Create table to store Admin details |  | Trainee_3 |  | 3 | 3 | 0.5 | 0.5 | 0 | 0
Task_2 | Design the Admin registration page |  | Trainee_4 |  | 3 | 5 | 5 | 1 | 1 | 1
Task_3 | Develop code for authentication |  | Trainee_3 |  | 2 | 2 | 5 | 0 | 1 | 0
Task_4 | Develop code to store the admin details |  | Trainee_4 |  | 5 | 5 | 9 | 5 | 1 | 0
US_3 | Listing courses | 5
Task_1 | Develop code for Admin or vendor to add a course |  | Trainee_1 |  | 8 | 6 | 0 | 0 | 0 | 0
Task_2 | Develop Code ofr Admin or vendor to edit a course |  | Trainee_2 |  | 3 | 1 | 3 | 3 | 3 | 0
Task_3 | Develop code for - On clicking on edit a form should be pop up With valid input clicking on Add/update will update the database |  | Trainee_3 |  | 1.5 | 1 | 0.5 | 0.5 | 1 | 1
Task_4 | Develop code for Admin or vendor to activate or deactivate a course |  | Trainee_4 |  | 2 | 0.5 | 0 | 0 | 0 | 0
US_4 |  | 8
Task_1 |  |  |  |  | 9 | 4 | 2 | 2 | 1 | 1
Task_2 |  |  |  |  | 6 | 6 | 3 | 3 | 3 | 1
Task_3 |  |  |  |  | 6 | 2 | 8 | 8 | 1 | 0
Task_4 |  |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0
US_5 |  | 3
Task_1 |  |  |  |  | 2 | 1 | 1 | 1 | 0.5 | 1
Task_2 |  |  |  |  | 6 | 6 | 6 | 0.5 | 3 | 9
Task_3 |  |  |  |  | 9 | 9 | 9 | 4 | 3 | 3
Task_4 |  |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0
TOTAL |  |  |  |  | 78 | 60 | 59 | 41 | 20 | 18

## Sprint -1
Sprint Backlog <My Tutor> Project ID: <A038> C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #1 | User Registration | 8
Task_1 | Create table to store registration details |  | Meghana | Completed | 7 | 5 | 3 | 0 | 0 | 0
Task_2 | Design the registration page |  | Padmasree | Completed | 3 | 1 | 1 | 5 | 0 | 1
Task_3 | Design Login page |  | Harathi | Completed | 1 | 0.5 | 0 | 3 | 0 | 0
Task_4 | Saving date in Database |  | Meghana | Completed | 0.5 | 1 | 2 | 3 | 1 | 0
User Story #2 | User Authenticatin | 8
Task_1 | Design user login |  | Vinay | Completed | 3 | 3 | 0.5 | 0.5 | 0 | 0
Task_2 | Validation against the database |  | Saiteja | Completed | 3 | 5 | 5 | 1 | 1 | 1
Task_3 | Showing error message |  | Meghana | Completed | 2 | 2 | 5 | 0 | 1 | 0
User Story #3 | Admin Credentials | 8
Task_1 | Design Admin login |  | Padmasree | Completed | 4 | 4 | 0.5 | 0.5 | 0 | 0
Task_2 | Admin credentials stored in Database |  | Meghana | Completed | 3 | 5 | 5 | 1 | 1 | 1
Task_3 | Showing error message |  | Harathi | Completed | 2 | 2 | 5 | 0 | 1 | 0
User Story #4 | User help | 3
Task_1 | Create table to store |  | Vinay | Completed | 3 | 3 | 0.5 | 0.5 | 0 | 0
Task_2 | Tickets saving to database |  | Harathi | Completed | 3 | 5 | 5 | 1 | 1 | 1
Task_3 | Portal display to report issues |  | Saiteja | Completed | 2 | 2 | 5 | 0 | 1 | 0
Task_4 | Admin viewable page |  | Padmasree | Completed | 5 | 5 | 9 | 5 | 1 | 0
User Story #5 | Admin resolve help request | 3
Task_1 | Develop code to resolve the issues |  | Harathi | Completed | 4 | 4 | 0.5 | 0.5 | 0 | 0
Task_2 | Connect to database |  | Meghana | Completed | 3 | 5 | 5 | 1 | 1 | 1
User Story #6 | User logoff | 8
Task_1 | Design a code to logoff |  | Meghana | Completed | 7 | 5 | 3 | 0 | 0 | 0
User Story #7 | User Password reset / Retrieve User ID | 5
Task_1 | Develop a code to fill Secret questions |  | Meghana | Completed | 3 | 5 | 5 | 1 | 1 | 1
Task_2 | Develop a code to rest password |  | Padmasree | Completed | 2 | 2 | 5 | 0 | 1 | 0
Task_3 | Validate in Database |  | Harathi | Completed | 5 | 5 | 9 | 5 | 1 | 0
User Story #8 | Tutor Details | 8
Task_1 | Sign in page for Tutor |  | Vinay | Completed | 7 | 5 | 3 | 0 | 0 | 0
Task_2 | Develop code to update skills |  | Saiteja | Completed | 3 | 1 | 1 | 5 | 0 | 1
Task_3 | Connection to database |  | Padmasree | Completed | 1 | 0.5 | 0 | 3 | 0 | 0
User Story #9 | Tutor edit timeslot | 8
Task_1 | Create code for timeslot |  | Meghana | Completed | 3 | 5 | 5 | 1 | 1 | 1
Task_2 | Create table to store booked timeslot |  | Meghana | Completed | 2 | 2 | 5 | 0 | 1 | 0
Task_3 | Saving data in database |  | Harathi | Completed | 5 | 5 | 9 | 5 | 1 | 0
User Story #10 | Student request skill | 8
Task_1 | Design code to request skill for student |  | Padmasree | Completed | 7 | 5 | 3 | 0 | 0 | 0
Task_2 | Design code to request skill for student |  | Vinay | Completed | 3 | 1 | 1 | 5 | 0 | 1
User Story #11 | Student select timesheet | 8
Task_1 | Create table to store timeslot |  | Saiteja | Completed | 7 | 5 | 3 | 0 | 0 | 0
Task_2 | Display the message by database |  | Harathi | Completed | 3 | 1 | 1 | 5 | 0 | 1
TOTAL |  |  |  |  | 48.5 | 52.5 | 52 | 22 | 9 | 5

## Sprint -2
Sprint Backlog <My Tutor> Project ID: <A038> C3: Protected Controlled Copy
BACKLOG TASK & ID | USER STORY & TASK | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
User Story #12 | Admin add topics | 8
Task_1 | Design code to add topics |  | Meghana | Completed | 7 | 5 | 3 | 0 | 0 | 0
Task_2 | Create table to store topics |  | Meghana | Completed | 3 | 1 | 1 | 5 | 0 | 1
Task_3 | Connection to database |  | Harathi | Completed | 1 | 0.5 | 0 | 3 | 0 | 0
Task_4 | Shows validation message |  | Vinay | Completed | 0.5 | 1 | 2 | 3 | 1 | 0
User Story #13 | Admin update topics | 5
Task_1 | Create table to show all topics |  | Padmasree | Completed | 4 | 4 | 0.5 | 0.5 | 0 | 0
Task_2 | Edit and update topics |  | Meghana | Completed | 3 | 5 | 5 | 1 | 1 | 1
Task_3 | Shows validation message |  | Vinay | Completed | 2 | 2 | 5 | 0 | 1 | 0
User Story #14 | Student submit papers | 8
Task_1 | Design code to submission page |  | Harathi | Completed | 7 | 5 | 3 | 0 | 0 | 0
Task_2 | Create table to store topics for paper submission |  | Saiteja | Completed | 3 | 1 | 1 | 5 | 0 | 1
Task_3 | Design code to upload the pdf |  | Padmasree | Completed | 1 | 0.5 | 0 | 3 | 0 | 0
Task_4 | Appropriate message should be displayed |  | Harathi | Completed | 0.5 | 1 | 2 | 3 | 1 | 0
User Story #15 | Tutor view papers | 8
Task_1 | Create table to show topics |  | Padamsree | Completed | 3 | 5 | 5 | 1 | 1 | 1
Task_2 | Design codeto Click the pdf |  | Harathi | Completed | 2 | 2 | 5 | 0 | 1 | 0
User Story #16 | Tutor provide reviews | 3
Task_1 | Design code to review submitted topics |  | Harathi | Completed | 3 | 5 | 5 | 1 | 1 | 1
Task_2 | Connect to database |  | Meghana | Completed | 2 | 2 | 5 | 0 | 1 | 0
Task_3 | Appropriate message should be displayed |  | Padmasree | Completed | 5 | 5 | 9 | 5 | 1 | 0
User Story #17 | Student view reviews | 3
Task_1 | Design code to view review page |  | Vinay | Completed | 3 | 5 | 5 | 1 | 1 | 1
Task_2 | Comments save to database |  | Vinay | Completed | 2 | 2 | 5 | 0 | 1 | 0
Task_3 | Appropriate message should be displayed |  | Saiteja | Completed | 5 | 5 | 9 | 5 | 1 | 0
User Story #18 | Admin reporting | 3
Task_1 | Design code to redirect to reporting page |  | Saiteja | Completed | 3 | 1 | 1 | 5 | 0 | 1
Task_2 | Design code to report for papers submitted |  | Harathi | Completed | 1 | 0.5 | 0 | 3 | 0 | 0
Task_3 | Reviews on papers |  | Meghana | Completed | 0.5 | 1 | 2 | 3 | 1 | 0
User Story #19 | Tutor classroom training details
Task_1 | Design code to add class room training details |  | Padmasree | Completed | 3 | 3 | 0.5 | 0.5 | 0 | 0
Task_2 | Create table to store data |  | Padmasree | Completed | 3 | 5 | 5 | 1 | 1 | 1
Task_3 | Save to database |  | Meghana | Completed | 2 | 2 | 5 | 0 | 1 | 0
User Story #20 | Student view/register for training | 8
Task_1 | Create table to store training details |  | Harathi | Completed | 7 | 5 | 3 | 0 | 0 | 0
Task_2 | Error message should be displayed |  | Harathi | Completed | 3 | 1 | 1 | 5 | 0 | 1
Task_3 | Design code to register for training |  | Meghana | Completed | 1 | 0.5 | 0 | 3 | 0 | 0
Task_4 | Create table to store available slots |  | Padmasree | Completed | 0.5 | 1 | 2 | 3 | 1 | 0
User Story #21 | Tutor view registration | 8
Task_1 | Design code to display all active trainings |  | Harathi | Completed | 3 | 1 | 1 | 5 | 0 | 1
Task_2 | Design code to displaystudent details by entering training ID |  | Meghana | Completed | 1 | 0.5 | 0 | 3 | 0 | 0
TOTAL |  |  |  |  | 85 | 78.5 | 91 | 68 | 16 | 10

## Data (hidden)
In-Progress
Completed
N/A